Event Title --Staffing Timeline Template

Location: 	Building --- Room Location

Time: 		Start Time – End Time

3:30 p.m. 	Set up begins (1 hour before lecture start time)

Staff: (2) volunteers for set up, (1) class tech

Supplies: 1 chair per speaker, 1 table between each chair. Water glass/bottle per speaker. 5 minute sign. Reserved tents as needed. Directional signage. Pre-lecture slide show and backing slide, post-it notes, sharpie

Tech: Check lavalier and wireless mics. Set up PPT display. Check in-room recording if using

Roles/Responsibilities: (1) staff to set signage, stage, audience. (1) staff to review tech and introductions/timelines. Review stage seating, label each mic with name of speaker, side the mic should go on (for lapel mics). Set reserved tents as needed (Q/A, Event Lead, etc). Set 5 minute warning sign at event lead’s seat with reserved tent. Set hand held mic for Q/A staff assistance seat. Set up welcome signage outside door, directional signage around building if using.

4:00 p.m.	Doors open (30 minutes before lecture start time)

Staff: (2) volunteers

Roles/Responsibilities: (1) staff at each entrance, greeting and answering questions. (1) staff escorting speakers

4:20 p.m.	Speakers arrive

Staff: (2) volunteers

Roles/Responsibilities: (1) staff in room, setting up backing slides from pre-lecture slide show, brings mics to speakers then returns to doors. (1) staff with speakers, sets up mics, confirms order, reviews event timeline and escorts inside.

4:30 p.m.	Event begins

Staff: (2) volunteers

Roles/Responsibilities: (1) staff escorts in speakers, (1) staff intro remarks

5:15 p.m. 	Panel concludes – Q&A begins

Staff: (1-2) volunteer

Role/Responsibility: (1) staff gives 5 minute wrap up sign, then 1-2 Q&A mic runners stand up and pass around mics

5:25 p.m.	Q&A concludes – closing remarks by [Name of Speaker]

5:30 p.m.	Event concludes – breakdown begins

Staff: (2) staff

Roles/Responsibilities: (1) staff to collect microphones, shut down PPT display, clear water glasses and bottles, collect signage and reserved tents. All available to bring chairs and tables back to events suite.