XPRIZE HEALTHSPAN SEMI-FINALS TIMELINE EXAMPLE

|  | 2025 Q1 |  |  | 2025 Q2 |  |  | 2025 Q3 |  |  | 2025 Q4 |  |  | 2026 Q1 |  |  | 2026 Q2 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MONTH | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| XPRIZE MILESTONE 1 JUDGING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Administrative Checks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Judges Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Semi-Finalist Notifications / Awards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| START-UP PHASE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Team & Investor Summit |  |  |  | TBD | TBD |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Clinical Protocol Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Regulatory Approvals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Staff Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECRUITMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Participant Recruitment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Baseline Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Intervention |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Follow-Up Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DATA ANALYSIS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Analyze Clinical Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Analyze PK/PD or Biomarker Data (if needed) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Finalize Data and Analyses |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DATA SUBMISSION & FINALS APPLICATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Deadline: Submit Results Package |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Deadline: Submit De-Identified Data Files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Deadline: Submit Finals Testing Application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE MILESTONE 2 JUDGING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Administrative Checks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE DCC Verification and Collate Results |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Judges Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| XPRIZE Finalist Notifications and Awards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Judging Questions on Timeline:

- Is the study timeline adequately described, taking into account start-up activities, recruitment, and planned assessment for Semi-Finals?

- Is there a proposed plan for how the Semi-Finals studies will expedite transition to Finalists’ 1-year clinical trials?

- Are regulatory materials prepared or approvals in process, and is this included in the proposed 1-year timeline?

- Are strategies in place should regulatory timelines be missed or delayed?

- Does the project incorporate efficiencies and utilize existing resources to increase the rate of participant enrollment, study start-up, and data collection, as appropriate?

- Are potential challenges that may impact timeline and corresponding solutions discussed in Qualifying Submission?