| ACCREDITATION TIMELINE TOOL |  |  |
| --- | --- | --- |
| Timeline (Countdown) | Key Events | Description |
| Start | Register with accreditation agency | - Options of Accreditation Agencies - Registration certificate, username/password – access to Accreditation website - Copy of RACGP 5th Standards |
| Receipt of registration certificate | Apply for the Practice Incentives Program (PIP) | - Visit PIP on Dept Of Health Website |
| 12 months | Self-assessment | - Go through self-assessment and identify gaps - Organise staff and clinical meetings at regular intervals - Start preparation of the Policy and procedure manual & - Computer Information & Security (CIS) manual - Book in patient feedback surveys - Clinical Audit Tool installation (QI component – can use Pen CAT) – review reports quarterly at staff and clinical meeting. |
| 11 months | Tasks | - Develop priority list based on gaps identified in the self-assessment - Assign a team members’ name next to each task - Assign due date next to each task/name - Create agenda for meetings – accreditation should be a standing agenda item. - Review equipment requirements – purchase/service - Review practice facilities requirements |
| 10 months | Tasks | - Review the delegation list monthly during meetings - Book in CPR for staff (renewed 3 yearly) - Book in continuing education for staff (Online cold chain & infection control) - Ensure signage/posters (refer to list provided by SWSPHN) and/or electronic health information (Med Channel/Tonic Health Media) |
| 6 months | Final Review | - Conduct final review of accreditation criteria using self-assessment online tool. - Book survey visit with accreditation agency - Review feedback from surveys and set up QI register to work on improvements - Develop/Review Practice information sheet - Ensure Recall/Reminder system - Implement Cold Chain Management and Infection Control system - Ensure evidence of staff qualifications including CPR training |
| 4 months | Preparation | - Ensure relevant staff are available on the day of accreditation visit - Designate responsible staff for all key areas required by the Standards - Have all documents/policies/templates completed and reviewed - Ensure all electronic resources are saved in an easily accessible location - Send Admin staff, Clinical staff and Doctors review notes - ask PSO - Accreditation checklist for physical environment requirement |
| 2 - 1 months | Preparation | - Ensure voicemail covers emergency details and After-hours details - Ensure no expired medications in the practice |
| Survey Day |  | - Make sure a room is set aside for the surveyors to work in - Ensure relevant staff members are on duty for the visit - Have all documents/policies/templates readily available |
| 1 month post | Results notification | - A full accreditation certificate and report will be issued, or - Conditional accreditation with list of recommendations given |
| 1 - 2 months post | Remedial action | - If conditional accreditation is issued: - Undertake remedial action - Supply evidence as required by assessment report - Process completion - If a full accreditation certificate is issued: - Accreditation achieved |
| 2+ months post | Ongoing process | - In between accreditation cycles, continue to update processes, procedures, policies in response to feedback and changes in the practice. |

Please note: This is a support timeline tool that is to be used only as a general guide.

Other resources available upon request:

- The 5th Accreditation Focus List

- Poster/Signage Checklist

- Template & Resources

- Accreditation Environment Checklist

- Admin staff, Clinical staff and Doctors review notes

- Online training options