EXAMPLE PROJECT MANAGEMENT TIMELINE – PROJECT NAME 2024

| ACTIVITY DESCRIPTION |  |  |  |
| --- | --- | --- | --- |
| Production and release of Project Name by John Smith, an experimental jazz album with accompanying artwork by Rei Hino. |  |  |  |
| PERSONNEL |  |  |  |
| Name | Role |  | Notes |
| John Smith | Artist, Project Lead |  | Confirmed |
| Jane Doe | Producer |  | In negotiation |
| Rei Hino | Digital Artist |  | Confirmed |
| Y Company | Marketing/Promo |  | Confirmed |
| RISKS |  |  |  |
| Production or artwork late, or further revisions required |  | Contingency buffers included in timeline - promo can also be pushed back if needed |  |

| Detailed Timeline |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Date | Activity Title | Description | Location | Who is involved | Outcomes | Task lead |  | Additional notes / Access requirements |  |
| 15/09 – 12/12 | Production period | Mixing/Mastering | Castlemaine | Jane Doe, John Smith | Final tracks | John Smith |  | Includes one week contingency for any unforeseen delays |  |
| 20/10 | Draft/Concept meeting | Initial samples and idea | Zoom | John Smith, Rei Hino | Confirm project timeline, Draft concept art | John Smith |  | Auslan interpreter to be engaged |  |
| 20/10 - 24/12 | Artwork development | Rei to develop accompanying artwork | Melton | Rei Hino | Concept art, Final artwork | Rei Hino |  | Includes two weeks contingency for any unforeseen delays |  |
| 10/11 10/12 31/12 | Check-in meetings | Check-ins on production, artwork, etc. | Zoom | John Smith, Jane Doe, Rei Hino |  | John Smith |  | Auslan interpreter to be engaged |  |
| 18/11 | Concept art review | Review of concept art, feedback, etc. | Zoom | John Smith, Jane Doe, Rei Hino | Final artwork | John Smith |  | Auslan interpreter to be engaged |  |
| 5/1 - 15/1/25 | Pre-release marketing | Promotional work - see marketing plan support doc | Online | John Smith, Y Company | Social media promotion, Targeted ads | Y Company |  | Can be pushed back 1-2 weeks as needed |  |
| 30/01/25 | Release | Album launch | Melbourne | John Smith, Rei Hino | Launch | John Smith |  |  |  |

| PROJECT TIMELINE (FUNDED PERIOD: 15 SEPTEMBER– 31 DECEMBER 2024) Details listed in timeline table below. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | SEPTEMBER |  | OCTOBER |  | NOVEMBER |  | DECEMBER |  | JANUARY |  |
|  | 1-15th | 16-30th | 1-15th | 16-31st | 1-15th | 16-30th | 1-15th | 16-31st | 1-15th | 16-31st |
| Activity Title | FUNDED PERIOD | FUNDED PERIOD | FUNDED PERIOD | FUNDED PERIOD | FUNDED PERIOD | FUNDED PERIOD | FUNDED PERIOD | FUNDED PERIOD | POST FUNDED PERIOD | POST FUNDED PERIOD |
| Kick-off Meeting |  |  |  |  |  |  |  |  |  | ALBUM LAUNCH |
| Production Period |  |  |  |  |  |  |  |  |  |  |
| Draft/Concept Meeting |  |  |  |  |  |  |  |  |  |  |
| Artwork Development |  |  |  |  |  |  |  |  |  |  |
| Concept Art Review |  |  |  |  |  |  |  |  |  |  |
| Check-in Meetings |  |  |  |  |  |  |  |  |  |  |
| Pre-release Marketing |  |  |  |  |  |  |  |  |  |  |