THE CHRONICLE OF PHILANTHROPY

A Timeline for Organizing a

Black-Tie Fundraising Gala

Want to be better organized? Visit philanthropy.com/resources for details about this and other tools.
Copyright © 2015 The Chronicle of Philanthropy

12 months in advance:

	Choose a chair for the event and nominate a steering committee.

	Set the date.

 	Decide on a budget

	Decide on a number of guests

	Identify additional fundraising activities for the event.

	Choose a theme.

	Choose, reserve a central, convenient, well-known venue.

	Hire entertainment.

	Reserve audio-visual equipment.

9 months before the event:

	Recruit subcommittee volunteers.

	Compile a list of potential major sponsors, and begin speaking with them.

 	Set table and ticket prices based on your fundraising goal.

	Select a caterer (unless venue has in-house catering).

	Begin sending letters requesting donations for significant auction items.

	Order decorations.

6 months before the event:

	Develop sponsorship packages for smaller donors.

	Choose the food and drink for the event, keeping in mind the gala’s theme for menu inspirations.

 	Make a floor plan.

	Start the guest list.

	Add the gala to your organization’s website and calendar.

	Design, print, and mail “save the date” cards.

	Choose the software or app you will use for event-management tasks.

	Confirm equipment to be provided by the venue and determine if any supplemental rentals are needed.

	Develop a publicity plan.

	Line up a host.

	Prepare auction-item contract forms for vendor and volunteer use.

	Hire a photographer.

3 months before the event:

	Design and print invitations.

	Draft and send out press releases and community notices announcing the gala.

 	Make sure all vendors are confirmed, contracts signed, and deposits paid.

	Finalize décor.

	Check in with sponsors.

	Set up the organization’s website to accept online payment for tickets and sponsorships.

	Set the lineup for the evening’s presentation.

	Design the program book.

	Design and print any banners or other signage desired for the event.

6 to 8 weeks before the event:

	Personalize and mail the printed invitations.

	Develop the event-night schedule.

 	Gather all sponsor names and logos and insert them into the program book.

	Begin gathering auction items.

1 month before the event:

	Finalize the event-night schedule, minute-by-minute.

	Complete and edit the program and auction books.

 	Generate bid sheets for the auction items.

	Follow up on any promised table sponsors who have not yet paid for their full or half tables.

	Arrange transportation.

	Check in with vendors one last time.

2 weeks before the event:

	Print the menu, program, and auction books.

	Develop seating charts.

	Get the final headcount of guests to the caterer and venue.

	Finalize videos and other presentation elements.

	Review remarks with the event’s host or master of ceremonies.

	Inspect auction items.

	Request the names of all guests seated at sponsored tables, rather than “John Smith and nine guests.”

1 week before the event:

	Finalize seating charts and print table cards.

	Confirm the arrival times of the entertainers.

	Confirm volunteer arrival times and assigned duties.

	Rehearse any presentations.

	Prepare electronic devices and software that will be used during the event.

	Prepare payments for vendors.

1 day before the event:

	Move decorations and auction items to the venue, if possible.

	Begin to decorate, if possible.

	Pack supplies. Fill a box with scissors, clear tape, duct tape, cord, push pins, permanent markers, and plenty of pens for the check-in and auction tables.

The day of the event:

	Be the first one on site.

	Ensure the check-in table is ready and staffed.

	Prepare the check-out table.

	Once everything is set up, walk through the venue, pretending you are an attendee.

During the event, with sample times:

	Check-in starts at 6 p.m. Give guests their auction number, drink tickets, etc.

	Start the happy hour and silent auction. 60 to 90 minutes.

	Open the doors to the dining room at 7:30 pm. Silent auction ends.

	Begin dinner at 8 p.m.

	Time the program to begin when dinner has been cleared but before dessert is served.

	Start the live auction, if you are having one.

	Dance floor opens at 9:30 or 10 p.m. Be sure auction checkout is open and ready for business.

	Event concludes midnight.

Immediately after the event:

	Clean up and stow any unclaimed auction items in a safe place.

	Check out vendors as they finish their pack-out to be sure they have left things clean.

	Return all rented or borrowed equipment.

Within 2 weeks after the event:

	Write thank-you notes to all attendees, volunteers, and sponsors.

	Send tax-deduction information.

	Evaluate the event.