Timeline Template and Example

|  | YEAR 1 |  |  |  | YEAR 2 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Pre-intervention |  |  |  |  |  |  |  |  |
| Participant Recruitment | x | x | x |  |  |  |  |  |
| Provider Education & Plenary sessions | x |  |  |  |  |  |  |  |
| Intervention |  |  |  |  |  |  |  |  |
| Group 1 |  | x |  |  |  |  |  |  |
| Group 2 |  |  | x |  |  |  |  |  |
| Group 3 |  |  |  | x |  |  |  |  |
| Post-Intervention |  |  |  |  |  |  |  |  |
| Group 1 follow-up |  |  | x |  |  |  |  |  |
| Group 2 follow-up |  |  |  | x |  |  |  |  |
| Group 3 follow-up |  |  |  |  | x |  |  |  |
| Data analysis |  |  |  |  | x | x | x |  |
| Intervention team interviews |  |  |  |  | x |  |  |  |
| Control groups offered intervention |  |  |  |  | x | x | x |  |
| Knowledge Translation |  |  |  |  |  |  |  |  |
| Engaging stakeholders |  |  |  | x |  | x | x | x |
| FM Community seminar |  |  |  |  |  |  | x |  |
| Research presentations |  |  |  |  |  |  | x |  |
| Final report & manuscript |  |  |  |  |  |  | x | x |
| Research team meetings | x | x |  | x |  | x |  | x |